## Introduction
Object Oriented Programming Project Management Sheet
Use this sheet to manage your project. It consists of the following tabs:
(1) | TaskList | The recorder maintains this worksheet To Start: Make your list of user stories Assign a priorit to each story from the dropdown list Estimate the time required for each story Set the status of each story to 1 as ToDO Set the % Done of each story to 0 as it has not been started yet At the start of each sprint: Choose which stories to focus on for the current sprint Set dues dates for each story Assign owners to each story Change the status of chosen stories to -1 for in progress At each session during a sprint: Check the progress of each story and change the % done accordingly Change the status of complete stories Log any comments, issues or new stories that have emerged
(2) | Burndown | The SCRUM master maintains this tab during the sprint. At the end of each session the amount of work in hours left to be completed is taken from the tasklist and rekeyed into this tab. By recording the work left to do the burn down chart for the team can be viewed which shows the estimated amount of work that needs to be completed before the project delivery date. The main activities and deliverables of each meeting should be recorded here. Looking at the graph it is obvious when additional resources are needed, or the current resources need to do more hours or the scope of the work is too big for the timeline - so a feature may need to be dropped.
(3) | Control | The control sheet contains the values that are used in the cell drop down Before starting the project replace the Resources section entries with the names of your team
(4) | Example | This tab shows an example of a filled in burn down chart where each day the hours left to be completed was noted.
This value here is the one to rekey into the burndown sheet
Put your names here
Goto Tasklist
Goto Burndown
Goto Control
Goto Example
Goto Resources

## TasksList
| TASKS LIST |  |  | Status : 1 = todo, -1 = doing, 0 = complete, d = deleted |  |  | Each day transfer burndown value to burn down sheet
|  |  |  | Estimated |  |  | Enter date | 0
Ref | Type | Stories | Priority | Hours to do | Status | % Done | Due By | BurnCalc | Sprint | Owner | Comment | Issues encountered | If Demoted explain why
US-0001 | Requirements & Design | Talk with secondary school students to discover what part or maths and science they find most difficult and how they think an mobile phone app might help OR ask tell them your idea and see what they think | 1 | 12 | 0 | 100% | 2012-02-07 | 0 | Sprint 0 - concept & plan | Tester1
US-0002 | Planning | Brain Storm ideas | 1 | 0.5 | 0 | 100% | 2012-02-07 | 0 | Sprint 0 - concept & plan | Tester1
US-0003 | Requirements & Design | As a student I want the app to be easy and accesable to all. | 1 | 0.5 | 0 | 100% |  | 0 | Sprint 0 - concept & plan | Tester1
US-0004 | Planning | As a group we Finalised Idea (Interactive log tables) | 1 | 0 | 0 | 100% | Tue 07 Feb | 0 | Sprint 0 - concept & plan | Developer2
US-0005 | Requirements & Design | designing interface | 1 | 2 | 0 | 100% | Thu 09 feb | 0 | Sprint 0 - concept & plan | Artist1
US-0006 | Build release | Gui of intergration | 1 | 1 | 0 | 100% | Thu 16 feb | 0 | Sprint 1 - build 1 | Developer3
US-0007 | Build release | Design of GUI for geometery and main GUI | 1 | 1 | 0 | 100% | Thu 16 feb | 0 | Sprint 1 - build 1 | Artist1
US-0008 | Build release | Design of GUI for Algebra and trigonometery GUI | 1 | 1 | 0 | 100% | Thu 16 feb | 0 | Sprint 1 - build 1 | Developer2
US-0009 | Planning | elect new scrummaster and notetaker | 1 | 1 | 0 | 100% | Thu 16 feb | 0 | Sprint 1 - build 1 | Tester1
US-0010 | Build release | Having more functionailty to GUI | 1 | 1 | 0 | 100% | Thu 23 | 0 | Sprint 1 - build 1 | Artist1
US-0011 | Requirements & Design | adding more design and images to are GUI also to add more buttons for fuctionality | 1 | 2 | 0 | 100% | tues 21 feb | 0 | Sprint 2 - build 2 | Developer1
US-0012 | Requirements & Design | Research individual class information eg formulas etc | 1 | 1 | 0 | 100% | tues 21 feb | 0 | Sprint 2 - build 2 | Tester1
US-0013 | Build release | Re-do of Gui | 1 | 1.5 | 0 | 100% | Tuesday 21 feb | 0 | Sprint 2 - build 2 | Kevin Gleeson
US-0014 | Build release | Differentiation Gui | 1 | 1 | 0 | 100% | Tuesday 21 feb | 0 | Sprint 2 - build 2 | Gareth harte
US-0015 | Build release | MainFrame Gui | 1 | 1 | 0 | 100% | Tuesday 21 feb | 0 | Sprint 2 - build 2 | Andy Dillon
US-0016 | Build release | Algebra and Trigonometery Gui | 1 | 1 | 0 | 100% | Tuesday 21 feb | 0 | Sprint 2 - build 2 | Cian Ellwood
US-0017 | Build release | Intergration Gui | 1 | 1 | 0 | 100% | Tuesday 21 feb | 0 | Sprint 2 - build 2 | Kevin Gleeson
US-0018 | Build release | Statistics Gui | 1 | 1 | 0 | 100% | Tuesday 21 feb | 0 | Sprint 2 - build 2 | Gareth harte
US-0019 | Planning | Brainstorm new ideas to add a quiz/game too app | 1 | 1 | 0 | 100% | Tuesday 21 feb | 0 | Sprint 2 - build 2 | Gemma Brady
US-0020 | Research | Each member must return with indivual research for each of there classes | 1 | 1 | 0 | 100% | Tuesday 21 feb | 0 | Sprint 2 - build 2 | Gemma Brady
US-0021 | Testing | run Working Gui and upload to moodle | 1 | 0.5 | 0 | 100% | Tuesday 6 march | 0 | Sprint 2 - build 2 | Gemma Brady
US-0022 | Build release | Start coding each individual class | 1 | 2 | 0 | 100% | Tuesday 6 march | 0 | Sprint 2 - build 2 | Cian Ellwood
US-0023 | Requirements & Design | Design individual images to display formulas | 1 | 4 | 0 | 100% | Thursday 8 march | 0 | Sprint 2 - build 2 | Gareth harte
US-0024 | Requirements & Design | adding background images to gui | 1 | 1 | 0 | 100% | Thursday 8 march | 0 | Sprint 2 - build 2 | Kevin Gleeson
US-0025 | Requirements & Design | Add icons to make app more appealing | 1 | 1 | 0 | 100% | Thursday 8 march | 0 | Sprint 2 - build 2 | Kevin Gleeson
US-0026 | Bug Fixing | Fix automatic resizing of GUI | 1 | 1 | 0 | 10% | Tuesday 13 march | 0 | Sprint 2 - build 2 | Gareth harte
US-0027 | Requirements & Design | Research and photoshop of formulas gareth and andy | 1 | 3 | 0 | 20% | Tuesday 13 march | 0 | Sprint 2 - build 2 | Andy Dillon
US-0028 | Requirements & Design | begin Flash cards class | 1 | 2 | d | 5% | Tuesday 13 march | 0 | Sprint 2 - build 2 | Gemma Brady
US-0029 | Requirements & Design | Trigonometery photoshop of formulas | 1 | 1 | 0 | 100% | Tuesday 13 march | 0 | Sprint 2 - build 2 | Gareth harte
US-0030 |  | add photoshopped pictures and Icons to GUI | 1 | 1 | 0 | 100% | Thursday march | 0 | Sprint 3 - build 3 | Gareth harte
US-0031 |  | Repair Flash Cards | 1 | 1 | d | 40% | Thursday 12 th march | 0 | Sprint 4 - test and fix | Gemma Brady
US-0032 |  | Add arrays to project to gain more marks | 1 | 1 | 0 | 13% | Thursday 12th march | 0 | Sprint 4 - test and fix | Kevin Gleeson
US-0033 |  | Fix resizing of Gui again | 1 | 0.5 | 0 | 100% | Thursday 12th march | 0 | Sprint 4 - test and fix | Kevin Gleeson
US-0034 |  | Complete burndown chart and last few task lists | 1 | 0.5 | 0 | 100% | Thursday 12th march | 0 | Sprint 4 - test and fix | Gemma Brady
US-0035 |  | Complete scrum board and send to Kevin for submission | 1 | 1 | 0 | 100% | Thursday 12th march | 0 | Sprint 4 - test and fix | Gemma Brady
US-0036 | [7 empty] | 0
US-0037 | [7 empty] | 0
US-0040 | [7 empty] | 0
US-0041 | [7 empty] | 0
US-0042 | [7 empty] | 0
US-0043 | [7 empty] | 0
US-0044 | [7 empty] | 0
US-0045 | [7 empty] | 0
US-0046 | [7 empty] | 0
US-0047 | [7 empty] | 0
US-0048 | [7 empty] | 0
US-0049 | [7 empty] | 0
US-0050 | [7 empty] | 0
US-0051 | [7 empty] | 0
US-0052 | [7 empty] | 0
US-0053 | [7 empty] | 0
US-0054 | [7 empty] | 0
US-0055 | [7 empty] | 0
US-0056 | [7 empty] | 0
US-0057 | [7 empty] | 0
US-0058 | [7 empty] | 0
US-0059 | [7 empty] | 0
US-0060 | [7 empty] | 0
US-0061 | [7 empty] | 0
US-0062 | [7 empty] | 0
US-0063 | [7 empty] | 0
US-0064 | [7 empty] | 0
US-0065 | [7 empty] | 0
US-0066 | [7 empty] | 0
US-0067 | [7 empty] | 0
US-0068 | [7 empty] | 0
US-0069 | [7 empty] | 0
US-0070 | [7 empty] | 0
US-0071 | [7 empty] | 0
US-0072 | [7 empty] | 0
US-0073 | [7 empty] | 0
US-0074 | [7 empty] | 0
US-0075 | [7 empty] | 0
US-0076 | [7 empty] | 0
US-0077 | [7 empty] | 0
US-0078 | [7 empty] | 0
US-0079 | [7 empty] | 0
US-0080 | [7 empty] | 0
US-0081 | [7 empty] | 0
US-0082 | [7 empty] | 0
US-0083 | [7 empty] | 0
US-0084 | [7 empty] | 0
US-0085 | [7 empty] | 0
US-0086 | [7 empty] | 0
US-0087 | [7 empty] | 0
US-0088 | [7 empty] | 0
US-0089 | [7 empty] | 0
US-0090 | [7 empty] | 0
US-0091 | [7 empty] | 0
US-0092 | [7 empty] | 0
US-0093 | [7 empty] | 0
US-0094 | [7 empty] | 0
US-0095 | [7 empty] | 0
US-0096 | [7 empty] | 0
US-0097 | [7 empty] | 0
US-0098 | [7 empty] | 0
US-0099 | [7 empty] | 0
US-0100 | [7 empty] | 0
US-0101 | [7 empty] | 0
US-0102 | [7 empty] | 0
US-0103 | [7 empty] | 0
US-0104 | [7 empty] | 0
US-0105 | [7 empty] | 0
US-0106 | [7 empty] | 0
US-0107 | [7 empty] | 0
US-0108 | [7 empty] | 0
US-0109 | [7 empty] | 0
US-0110 | [7 empty] | 0
US-0111 | [7 empty] | 0
US-0112 | [7 empty] | 0
US-0113 | [7 empty] | 0
US-0114 | [7 empty] | 0
The value will only change if you have completed or semi-completed some task
Back

## Burndown
Burn Down |  |  |  | Average daily hours: | 0 | resources: | 4 | Estimated Completion date
| Date | BurnCalc | General Activity | Deliverables | Team Hours | Recorder | ScrumMaster
Sprint 0
Req's Gathering | 2012-02-02 | 0.75
Concept | 2012-02-07 | 0.75
Design | 2012-02-09 | 0.75
UI Mock-up | 2012-02-14 | 0.75
Planning | 2012-02-16 | 5.4
Sprint 1 | 2012-02-21 | 1.8
Build 1 | 2012-02-23 | 10.4
| 2012-02-28 | 10.4
| 2012-03-01 | 7.25
Sprint 2 | 2012-03-06 | 10.4
Build 2 | 2012-03-08 | 6.8
| 2012-03-13 | 7.25
| 2012-03-15 | 6.25
Sprint 3 | 2012-03-20 | 8.1
Build 3 | 2012-03-22 | 8.1
| 2012-03-27 | 3.57
| 2012-03-29 | 3.57
Sprint 4 | 2012-04-03 | 1.8
Test & Debug | 2012-04-05 | 0.75
| 2012-04-10 | 1.8
| 2012-04-12 | 0.87 | Submission
Each day enter burn value here
this calculation is only correct if there are no filters on in the TaskList as it depends on the currently reported total hours of work
Back

## Control
| Project Control |  | Version: | 1 | Current Sprint: | 0 | Date: | 2012-04-13 14:32
Values used in cell dropdowns |  |  |  |  | Deliverables
| Source Type | Expected |  |  | D001
|  | Unexpected |  |  | D002
|  | New Feature |  |  | D003
D004
| Cost/Complexity | 3 hours / Simple |  |  | D005
|  | 10 hours / Medium |  |  | D006
|  | 25 hours / Complex |  |  | D007
D008
| Priority | 0 |  |  | D009
|  | 1 |  |  | D010
2
3
| User Story Type | Programming
Art / Sound Assets
Research
Build release
Testing
Requirements & Design
Bug Fixing
Planning
| Status | 1 | Incomplete
|  | -1 | In Progress
|  | 0 | Completed
|  | d | Demoted
| Resources | Andy Dillon | Andy Dillon
|  | Kevin Gleeson | Kevin Gleeson
Gareth harte
|  | Cian Ellwood | Cian Ellwood
|  | Gemma Brady | Gemma Brady
| Sprint | Sprint 0 - concept & plan
Sprint 1 - build 1
Sprint 2 - build 2
Sprint 3 - build 3
Sprint 4 - test and fix
Put your names here, replacing the templated text
Good to make a list of exactly what has to be delivered. So that it is in one place as a reminder of the projects objective
Back

## Example
| Burn Down |  |  |  |  | Sprint | 4
| Date | CostDue | Activity | Deliverables | SprintMaster
Sprint 0 | 2008-04-14 | 450 |  |  | Paul
| 2008-04-15 | 77 |  |  | Paul
| 2008-04-16 | 77 |  |  | Paul
| 2008-04-17 | 160 |  |  | Paul
| 2008-04-18 | 266 | Planning Meeting | Design Spec ( 4 pages ) | Paul
| 2008-04-19 | 266 |  |  | Paul
| 2008-04-20 | 266 |  |  | Paul
Sprint 1 | 2008-04-21 | 266 |  |  | Adam
| 2008-04-22 | 203 |  |  | Adam
| 2008-04-23 | 203 |  |  | Adam
| 2008-04-24 | 203 |  |  | Adam
| 2008-04-25 | 203 |  |  | Adam
| 2008-04-26 | 203 |  |  | Adam
| 2008-04-27 | 203 |  |  | Adam
Sprint 2 | 2008-04-28 | 406 | Planning Meeting | Build Demo | Mary
| 2008-04-29 | 413 |  |  | Mary
| 2008-04-30 | 378 |  |  | Mary
| 2008-05-01 | 371 |  |  | Mary
| 2008-05-02 | 229.25 |  |  | Mary
| 2008-05-03 | 220.1 |  |  | Mary
| 2008-05-04 | 215.95 |  |  | Mary
| 2008-05-05 | 171.5 |  |  | Mary
Sprint 3 | 2008-05-06 | 145.6 | Planning Meeting | Build Demo | James
| 2008-05-07 | 128.87 |  |  | James
| 2008-05-08 | 112.78 |  |  | James
| 2008-05-09 | 117.03 | Planning Meeting - Finish line |  | James
| 2008-05-10 | 103.48 |  |  | James
| 2008-05-11 | 90.78 |  |  | James
| 2008-05-12 | 73.07 | Planning Meeting | Final Build | James
| 2008-05-13 |  | Project Delivery (5pm) | XBOX360 Software, Documents | James
| 2008-05-14 |  | Project Presentation (10am) | Presentation Slides | James
Back